## Sheet1
Day | Task | Description
Day 1-2 | Set up development environment | Install necessary software (IDE, database, version control system). Initialize a version control repository (Git). Set up a basic project structure with folders for each module.
Day 1-2 | Define requirements and architecture | Create a detailed plan outlining features and their interdependencies. Sketch out the application architecture (frontend, backend, database).
Day 3-4 | Database schema design (User Management) | Create tables for users, roles, and permissions.
Day 3-4 | Backend setup (User Management) | Develop the user authentication and authorization system. Implement APIs for user registration, login, and role management.
Day 5-6 | Database schema design (Task Management) | Create tables for tasks, task assignments, and task statuses.
Day 5-6 | Backend setup (Task Management) | Implement basic CRUD (Create, Read, Update, Delete) operations for tasks. Develop APIs for task assignment and status updates.
Day 7-8 | Backend setup (Dashboard) | Implement the logic for aggregating task data (counts of active, completed, and overdue tasks).
Day 7-8 | Frontend setup (Dashboard) | Create a basic frontend interface (using a framework like React, Angular, or Vue). Develop the initial dashboard to display task statistics.
Day 9-10 | Integration (Frontend-Backend) | Connect the frontend to the backend APIs. Ensure user authentication and task management features are working together.
Day 9-10 | Testing (Functionality, Debugging) | Perform basic functionality testing for user registration, login, task creation, and task assignment. Debug and fix any issues encountered during testing.